## Final Risk Register – Vendora AI-Integrated Store

| ##### Risk ID | ##### Risk Description | ##### Category | ##### Prob. | ##### Impact | ##### RPN | ##### Priority | ##### Mitigation Strategy | ##### Contingency Plan | ##### Risk Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-07 | Checkout/order flow errors | Business/Tech | 3 | 3 | 9 | Critical | E2E testing, validation, order logic | Switch to manual order mode | Backend + QA |
| R-08 | AI API rate limits or downtime | External/Tech | 3 | 3 | 9 | Critical | Retry logic, caching, reduce calls | Use manual templates/disable AI | AI Developer |
| R-12 | Tight project deadline | Schedule | 3 | 3 | 9 | Critical | Daily standups, scope freeze | Drop low-priority features | Project Manager |
| R-01 | Auth/login system bugs | Technical | 2 | 3 | 6 | High | Test flows, validate sessions | Roll back to stable version | Backend Dev |
| R-03 | Product CRUD malfunction | Technical | 2 | 3 | 6 | High | Unit testing, code reviews | Disable feature/restore build | Full Stack Dev |
| R-10 | Payment gateway failure | External/Tech | 2 | 3 | 6 | High | Sandbox testing, secure API | Enable cash/manual fallback | Backend Dev |
| R-13 | Deployment/timeout issues | Deployment | 2 | 3 | 6 | High | Optimize APIs, pre-deploy tests | Roll back and redeploy | DevOps Lead |
| R-15 | Insufficient testing | Quality | 2 | 3 | 6 | High | Dedicated QA phase, checklists | Final bug-fix sprint | QA Lead |
| R-02 | Database inconsistency | Technical | 2 | 2 | 4 | Medium | Normalize schema, backup often | Restore backup, patch tables | Database Lead |
| R-04 | Image upload failures | Technical | 2 | 2 | 4 | Medium | Compress images, file validation | Use placeholder images | Frontend Dev |
| R-05 | Catalog/search slowdown | Performance | 2 | 2 | 4 | Medium | Pagination, indexing, lazy load | Simplify search/optimize queries | FE + BE Team |
| R-06 | Cart data not persisting | Technical | 2 | 2 | 4 | Medium | Test local storage/session logic | Use session-based temp cart | Frontend Dev |
| R-14 | Team miscommunication | Management | 2 | 2 | 4 | Medium | Use ClickUp, Git branches | Emergency meeting/redistribute | Team Lead |
| R-09 | Poor AI descriptions | Quality | 1 | 2 | 2 | Low | Manual override, prompt tuning | Sellers rewrite content | AI/Content Lead |
| R-11 | Incorrect dashboard data | Functional | 1 | 2 | 2 | Low | Validate queries, test metrics | Use raw database reports | Dashboard Dev |

### Risk Priority Summary

#### 1. Critical Risks (RPN: 9)

These require immediate, ongoing attention as they directly threaten the project's viability:

- R-07 (Checkout): A broken checkout is a non-functioning business.

- R-08 (AI Dependency): External API failures can paralyze AI-integrated features.

- R-12 (Deadline): The 30-day timeline leaves no room for scope creep.

#### 2. High Risks (RPN: 6)

Technical hurdles that can block specific user groups or deployment:

- R-01, R-03, R-10, R-13, R-15: Issues ranging from authentication and CRUD bugs to deployment timeouts and lack of testing.

#### 3. Medium & Low Risks (RPN: 2–4)

Internal performance and operational "noise":

- Medium: Data consistency, image storage, and team coordination.

- Low: Quality of AI output and minor dashboard inaccuracies.

### Final Statement

This register serves as the team's defensive playbook. By identifying these 15 risks early, Vendora moves from a theoretical WBS  to a practical, risk-aware development cycle.