# Risk Management Plan

## 1. Risk Identification

These risks are mapped to the core sections of the Vendora WBS, including Infrastructure, Engagement, and Core Platform development.

| ### Risk ID | ### Description | ### Related WBS Area |
| --- | --- | --- |
| R-01 | Bugs in login/authentication system | 2.1 Secure User Management |
| R-02 | Database schema issues/inconsistency | 1.3.2 Database Design |
| R-03 | CRUD product module malfunction | 2.2 Product Management |
| R-04 | Image upload failures/storage overflow | 2.2.4 / 5.2.1 |
| R-05 | Slow search/catalog performance | 2.3 Buyer Experience |
| R-06 | Shopping cart data persistence failure | 2.3.4 |
| R-07 | Checkout/order flow errors | 2.4 Order Processing |
| R-08 | AI API rate limits or downtime | 3.1 AI Assistant |
| R-09 | Poor AI-generated descriptions | 3.1 / 5.1.3 |
| R-10 | Payment gateway integration failure | 3.3 Financial Integration |
| R-11 | Dashboard displays incorrect data | 4.1 Dashboard |
| R-12 | Tight project deadline/delayed tasks | Entire Project |
| R-13 | Deployment/serverless timeout issues | 5.2.2 / 6.3.1 |
| R-14 | Team miscommunication/merge conflicts | 1.2 GitHub / ClickUp |
| R-15 | Insufficient testing before submission | 5.1 QA |

## 2. Risk Prioritization Matrix

We categorize risks by Probability (likelihood of occurring) and Impact (severity of the effect on the project).

| PROBABILITY / IMPACT → | Low Impact (1) | Medium Impact (2) | High Impact (3) |
| --- | --- | --- | --- |
| High (3) | — | — | R-07, R-08, R-12 |
| Medium (2) | — | R-02, R-04, R-05, R-06, R-14 | R-01, R-03, R-10, R-13, R-15 |
| Low (1) | — | R-09, R-11 | — |

Critical Zone: The top-right corner features the "Villain Trio": Checkout Failures (R-07), AI Dependencies (R-08), and Deadline Pressure (R-12). These have the highest potential to derail Vendora's delivery.

## 3. Top 5 Mitigation Strategies

- R-07 — Checkout/Order Flow (Mitigate): Implement strict end-to-end testing and backend validation to ensure every order is captured accurately.

- R-12 — Tight Deadline (Mitigate): Focus on "Must-Have" features first, freeze the scope early, and maintain a strict weekly milestone schedule.

- R-08 — AI API Issues (Mitigate + Accept): Use caching and fallback templates so the store remains functional even if the OpenAI/Gemini API is down.

- R-10 — Payment Failure (Mitigate): Utilize sandbox environments for testing and provide a manual payment/COD backup option.

- R-15 — Insufficient Testing (Avoid): Schedule dedicated QA cycles throughout the project rather than leaving all testing for the final night.

## 4. Risks Affecting the Critical Path

The critical path for Vendora follows the flow from Infrastructure Setup → Database Design → Core Development → AI Integration → Deployment.

- Deadline Delays (R-12): Any slip in the early WBS phases (like Infrastructure or Database) will immediately push back the final delivery.

- Checkout/Order Errors (R-07): As a late-stage core feature, errors here require extensive rework of previous database and API tasks.

- Deployment Blockers (R-13): Even a perfect build is a failure if the serverless infrastructure (Vercel) fails during the final push.

## Final Summary

To ensure Vendora transitions from a WBS to a live store, the team must prioritize stabilizing the checkout flow, managing the AI API integration, and adhering to a strict 30-day timeline. Successful mitigation prevents the project from becoming a "soul-expensive" recovery mission.